## 工作表1
|  | 2000 | 1500 | 1000 | 1150 | 1200 | 800 | 750 | 750 | 700 | 700 | 300 | 300
WBS No | WBS TASK Activities | CORP-CEO | EXECUTIVE | SENIOR USER | SENIOR SUPPLIER | PROJECT MANAGER | CHANGE MANAGER | BRAD - SEG1 | SIMONE - SEG2 | LORAINE - HEG1 | MARK - HEG2 | JAMES - CSEG1 | PENNY -CSEG2 | TIME (DAYS) | COST (wages)
1 | CMS SCM System Project
1.1 | Planning Phase
1.1.1 | *Problem Definition |  | R | AR | R | R | [7 empty] | 1 | 730
1.1.2 | *Listing Solution Adequacies |  | R | R | AR | R | [7 empty] | 1 | 730
1.1.3 | *Evaluating benefits to be realised from a solution |  | AR | R | R | R | [7 empty] | 1 | 730
1.1.4 | *Defining the scope of the project |  | R | R | R | AR | [7 empty] | 1 | 730
1.1.5 | *Define preliminary resources |  | R | R | AR | R | [7 empty] | 1 | 730
1.1.6 | *Risk Analysis |  | R | R | R | AR | [7 empty] | 2 | 730
1.1.7 | * Review staffing / HR requirements |  | R | R | R | AR | [7 empty] | 2 | 730
1.1.8 | *Review Customer Service & manufacturer delivery requirements |  | R | AR | R | R | [7 empty] | 1 | 730
[13 empty] | total | 10 | 5840
1.2 | Preliminary investigation phase
1.2.1 | *Review current processing |  | R | R | R | AR | [7 empty] | 1 | 730
1.2.2 | *Prepare organisational chart |  | R | R | R | AR | [7 empty] | 1 | 730
1.2.3 | *Cost benefit analysis |  | R | R | R | AR | [7 empty] | 2 | 7300
1.2.4 | *Time and cost estimates |  | R | R | R | AR | [7 empty] | 2 | 7300
1.2.5 | *Alternative solutions |  | R | R | R | AR | [7 empty] | 2 | 7300
1.2.6 | *Preparing feasibility report |  | R | R | R | AR | [7 empty] | 2 | 7300
[13 empty] | total | 10 | 30660
1.3 | Analysis Phase
1.3.1 | *Conduct needs analysis |  | R | AR | R | R | [7 empty] | 1 | 730
1.3.2 | *Draft preliminary software / hardware specifications |  | R | R | AR | R | [7 empty] | 2 | 365
1.3.3 | *API(s) review for applications & interconnect requirement |  | R | R | AR | R | [7 empty] | 1 | 365
1.3.4 | *Develop preliminary budget |  | AR | R | R | R | [7 empty] | 2 | 730
1.3.5 | *Review software/hardware specifications/budget with team |  | R | R | AR | R | [7 empty] | 2 | 7300
1.3.6 | *Incorporate feedback on software/hardware specifications |  | R | AR | R | R | [7 empty] | 1 | 365
1.3.7 | *Develop delivery timeline |  | R | R | R | AR | [7 empty] | 2 | 7300
1.3.8 | *Obtain approvals to proceed (concept, timeline, and budget) |  | AR | R | R | R | [7 empty] | 1 | 365
1.3.9 | *Secure Core Resources (Purchase IT Infrastructure) |  | R | R | AR | R | [7 empty] | 2 | 7300
1.3.10 | *Presentation to the user |  | R | R | AR | R | [7 empty] | 1 | 3650
[13 empty] | total | 15 | 28470
1.4 | Design phase
1.4.1 | *Review preliminary software/hardware specifications |  |  |  | AR |  |  | R | R | R | R | R | R | 1 | 450
1.4.2 | *Develop functional specifications |  |  |  | AR |  |  | R | R | R | R | R | R | 3 | 1350
1.4.3 | *Develop prototype based on functional specifications |  |  |  | AR |  |  | R | R | R | R | R | R | 3 | 3950
1.4.4 | *Risk Management |  | R | R | R | AR |  | R | R | R | R | R | R | 2 | 1300
1.4.5 | *Review functional specifications |  |  |  | AR |  |  | R | R | R | R | R | R | 2 | 300
1.4.6 | *Incorporate feedback into functional specifications |  |  |  | AR |  |  | R | R | R | R | R | R | 3 | 1950
1.4.7 | *Obtain approval to proceed/ Presentation to the user |  | AR | R | R | [8 empty] | 1 | 3650
[13 empty] | total | 15 | 12950
1.5 | Implementation phase
1.5.1 | *Acquiring new hardware and software |  | AR |  | R | R | R | R | R | R | R | R | R | 1 | 6950
1.5.2 | *Disconnecting the old computer |  |  |  | AR |  | R | R | R | R | R | R | R | 1 | 5450
1.5.3 | *Using a temporary server to maintain current system |  |  |  | AR |  | R | R | R | R | R | R | R | 1 | 5450
1.5.4 | *Disassembling furniture |  |  |  | AR |  | R | R | R | R | R | R | R | 1 | 5450
1.5.5 | *Moving furniture/equipment |  |  |  | AR |  | R | R | R | R | R | R | R | 1 | 5450
1.5.6 | *Installing new hardware and software |  |  |  | AR |  | R | R | R | R | R | R | R | 2 | 10900
1.5.7 | *Development Environment |  |  |  | AR |  | R | R | R | R | R | R | R | 3 | 1350
1.5.8 | *User Interface Design |  |  |  | AR |  | R | R | R | R | R |  |  | 2 | 9700
1.5.9 | *Database Model |  |  |  | AR |  | R | R | R | R | R |  |  | 1 | 4850
1.5.10 | *Database design |  |  |  | AR |  | R | R | R | R | R |  |  | 2 | 9700
1.5.11 | *Develop code |  |  |  | AR |  | R | R | R | R | R |  |  | 3 | 1550
1.5.12 | *Code Generation Release Testing Bug Fixes |  |  |  | AR |  | R | R | R | R | R |  |  | 3 | 1450
1.5.13 | *Test plan and Test Environment Setup |  |  |  | AR |  | R | R | R | R | R | R | R | 2 | 730
1.5.14 | *Developer Testing |  |  |  | AR |  | R | R | R | R | R | R | R | 1 | 5450
1.5.15 | *User Acceptance Testing |  |  | R | AR |  | R | R | R | R | R | R | R | 1 | 6450
1.5.16 | *Resolution of any problems |  |  |  | AR |  | R | R | R | R | R | R | R | 2 | 100
1.5.17 | *Preparation of documentation |  |  |  | AR |  | R | R | R | R | R | R | R | 1 | 5450
1.5.18 | *Release full system |  |  |  | AR |  |  | R | R | R | R | R | R | 2 | 9300
1.5.19 | *Results Reporting |  |  |  | AR | R | R | R | R | R | R | R | R | 1 | 5450
1.5.20 | *Training of customer service staff |  |  | R | AR |  | R | R | R | R | R | R | R | 2 | 1290
1.5.21 | *Deploy full System and Operations Switch Over |  |  |  | AR | R | R | R | R | R | R | R | R | 2 | 10900
[13 empty] | total | 35 | 113370
1.6 | Close-Out phase
1.6.1 | *Final report to management |  |  |  | R | AR | [7 empty] | 1 | 1150
1.6.2 | *Final presentation to the user |  |  |  | R | AR | [7 empty] | 1 | 1150
1.6.3 | *Customer acceptance |  | AR | [10 empty] | 2 | 3000
1.6.4 | *Lessons Learnt Report |  |  |  |  | AR | [7 empty] | 1 | ——
[13 empty] | total | 5 | 5300
[12 empty] | Project total | timeframe | 90 | Days
[12 empty] | TOYAL WAG E COST |  |  | 196590
[12 empty] | PROJECT MANAGER WAGE |  |  | 108000
[12 empty] | TOTAL PROJECT WAGE COST |  |  | 304590
[12 empty] | INFRASTRUCTURE COST |  |  | 120000
[12 empty] | SOFTWARE COST |  |  | 70000
[12 empty] | TESTING COST |  |  | 19000
[12 empty] | Training COST |  |  | 3800
[12 empty] | Reserve cost |  |  | 101797.5
[12 empty] | OVERALL BUDGET |  |  | 619187.5