## Sheet1
Project Name: |  |  | UAV Web System
Rank | Risk and Category | Root Cause | Risk Countermeasure and Response | Risk Owner | Probability | Impact
1 | Staff Missing:People | Unwell, injury, leaving | Mitigation:Improve staff relations,health programs,make sure working environment safe | Project Manager | HIGH | HIGH
2 | Hardware fails: Technology | Certain hardware is difficult to storage | Transference:Purchase special insurance or warranty protection for the specific hardware required | Senior Supplier | Medium | HIGH
3 | Absence of leadership: People | No leader found when needed | Acceptance: Dismiss the often absent leader,after the previous project manager withdrew, a new person was assigned to lead the project. | Change Manager | Low | High
4 | Unplanned Changes: Process | No Formal Change management Process | Avoidance:Make sure that the change managing process is in place and used | Change Manager | Medium | Medium
5 | Progress delay: process | Do not follow the plan, the progress is slow | Mitigation measures: increase the frequency of project monitoring. Use WBS and CPM to plan reasonable working hours and follow the schedule. Select the most experienced project manager. | Project Manager | Medium | Medium
6 | Changes in the market | Changes happen in market characteristics or demand | Avoidance: Analyze the market trend, carefully evaluate and review the project in the first stage to determine | Executive | Low | High
7 | Infrastructure damage: Technology | Data center loses power , the network goes down | Acceptance: execute emergency plan, start emergency plan or standby plan, start standby equipment, contact maintenance personnel for timely maintenance. | Senior Supplier | Medium | Medium